1. Purpose, Baselines and Categories

This register records every material difference between the system described in the project's three baseline documents and the system actually built and deployed as of 21 July 2026. It merges two comparison exercises:

- a project-management comparison against the Project Management Plan v1.0 (6 June 2026), and

- a line-level code review against the Design Document v5 (final revision dated 27 June 2026 in its version-control table) and the Requirements & Analysis submission.

Where specific files, line numbers or section texts are cited, each citation has been verified against the original document or source file.

Each entry is classified into one of five categories:

- Scope Addition - capability that exists in no baseline document and was added during development.

- Design Change - a baseline document specified one approach and the delivered system uses a different one.

- Scope Reduction - documented UI capability consciously reduced or simplified under the project timeline.

- Deferred - capability postponed and documented in future-work.md.

- Known Limitation - a residual constraint of the delivered system, recorded rather than solved.

Overall verdict of the code review: the structural skeleton - server-side JWT verification, dual JWT secrets, blacklist enforcement, and unconditional scan logging - was built exactly as designed, and in several places the implementation exceeds the documents. The divergences fall into the categories above and are individually justified below.

2. Scope Additions

A1  Full User Authentication System

Baseline:

- PMP 4.1.4 explicitly excluded end-user registration and login (“authentication is token-based at the QR code level”).

- R&A 4.1 defines the User actor as “unauthenticated individuals.”

As built:

- A complete custom authentication system shared by web and mobile: registration (single form, every account created as role 'user'), login, forgot-password and reset-password with single-use expiring tokens, and logged-in password change.

- The reset flow is channel-aware - admin accounts reset via the web, regular users via the mobile app, enforced server-side.

- Demo mode returns the reset link in the API response because no e-mail service is in scope.

- Passwords are hashed with bcrypt.

- Tamper reporting and destination access now require a signed-in account (no anonymous reports).

Rationale:

- The Admin Dashboard cannot be exposed publicly without authentication.

- Once accounts existed, extending them to app users enabled per-user scan history and attributable tamper reports.

- The browser (regular scanner) path remains account-free, preserving the original token-level promise for the public.

Impact:

- R&A 4.1 actor definitions must be re-worded (reporting and destination access require authentication).

- Final Report must present this as a deliberate scope extension.

A2  Dual JWT Architecture and authVersion Token Invalidation

Baseline: PMP WBS 3.4 specified a single token signing approach; neither Design nor R&A separates token types or defines session revocation.

As built:

- Two fully separated JWT types: QR tokens (QR_JWT_SECRET) inside printed codes, and auth tokens (AUTH_JWT_SECRET) for sessions - secrets never interchanged.

- Every User row carries an authVersion counter: password changes, password resets and role changes increment it, instantly revoking every previously issued JWT for that account.

Rationale:

- QR tokens are public by nature; sharing a secret with session tokens would let a printed artefact weaken account security.

- authVersion is the concrete realisation of R&A FR-02's “preventing replay-based misuse” - stronger than the documents require.

Impact: Architecture documentation must describe both secrets and the authVersion mechanism.

A3  User Administration

Baseline: No user administration exists in any baseline document (PMP WBS 5.3 lists Dashboard, QR Management, Alerts only).

As built:

- A Users page with search and pagination.

- Role promotion/demotion with a server-enforced last-admin demotion guard and a self-role-change block.

- Admin-created accounts (POST /api/admin/users, optional role).

- User deletion with transactional foreign-key cleanup (admins must first be demoted).

- First-admin seeding from environment variables - never hardcoded credentials.

Rationale: A direct consequence of A1: accounts require administration, and the system needs protection against locking out every administrator.

Impact:

- User Manual requires a user-administration chapter.

- The Design 4.6 CRUD matrix contains no Delete operation and omits admin-side creation - both must be added.

A4  Database Schema - Five Tables and Column-Level Deltas

Baseline: PMP WBS 3.2 and Design 4.2-4.4 define four entities (User, QR_Code, QR_Scan_Log, QR_Incident_Report) with NOT NULL constraints throughout.

As built:

Five tables: User, QrCode, ScanLog, Alert, plus ActivityLog (curated feed events: status_changed, alert_created, alert_resolved) powering the Recent Activity panel, while ScanLog remains raw telemetry - keeping the two separate is a settled decision. Column-level deltas found in code review:

- The Design data dictionary omits the email column entirely, although email is the login identifier - a documentation defect.

- Photo is documented as BYTEA NOT NULL but implemented as an optional photoUrl pointing to Supabase Storage. The Design Document contradicts itself: 4.3 says BYTEA while 6.5 selects cloud object storage - 4.3 is the section to correct.

- GPS moves from VARCHAR(255) NOT NULL to an optional gpsLat/gpsLng Float pair, validated as a pair when supplied.

- ScanLog.qrCodeId is deliberately nullable - a forged token has no matching QR record, yet the failed scan must still be logged because it is itself evidence of tampering.

- Alert.reportedById is optional with onDelete: SetNull so reports survive deletion of the reporter's account.

- Contact grows from VARCHAR(15) to 200 characters.

- Role values are lowercase admin/user rather than the documented capitalised forms.

- ScanLog gains userId (the basis of server-side scan history, B5).

- QrCode gains an optional label.

- The documented Validation_Outcome vocabulary lists four values (Valid, Invalid, Expired, Blacklisted) while the implementation records five - 'suspicious' is added as a distinct outcome.

Rationale:

- Every NOT NULL relaxation serves auditability: failed scans must be loggable, and audit records must survive account deletion.

- The ActivityLog split preserves both an analytics stream and a human-readable event feed.

Impact:

- Design 4.3 data dictionary and the ERD must be regenerated: add email and ActivityLog, replace BYTEA with photoUrl, update status vocabularies, and record the relaxed constraints.

- Logical-vs-physical type mapping (uuid/varchar/CHECK vs text with application-level validation) is documented in schema-reconciliation.md.

A5  QR Lifecycle States, Integrity Guards and On-Demand Image Regeneration

Baseline:

- PMP WBS 4.5.3 specifies a blacklist/whitelist check.

- Design 5.1 describes expiry as a temporal event.

- Design 6.4.2 states QR images are “generated once at creation time.”

As built:

A four-state lifecycle (active / suspicious / blacklisted / expired) with enforced rules:

- A lazy sweep - expireStaleQrCodes() - flips time-expired active codes to 'expired' on every admin read endpoint, since the passage of time alone never executes code.

- Expiry is terminal - the UI hides Activate/Blacklist for expired codes and the server rejects any status change on a time-expired code, because the expiry is baked into the printed JWT and no database value can revive the signature.

- A tamper report promotes a code to 'suspicious' only from 'active' - a user report can never downgrade an admin-confirmed 'blacklisted' verdict nor resurrect an expired code (users detect, administrators confirm).

- Contrary to Design 6.4.2, QR images are never stored: the PNG is regenerated on demand from the stored token.

Rationale:

- The sweep realises the documented 'temporal event' honestly.

- Regeneration keeps zero image storage and makes drift between image and token impossible - the system keeps the negative (the signed token) and re-prints on demand.

Impact: Design 5.1/6.4.2 and status-transition test cases must be updated to these rules.

A6  Operational Additions Absent from All Documents

As built:

- CSV export of all QR codes (GET /api/admin/qrcodes/export).

- The Recent Activity feed backed by ActivityLog.

- Period-over-period delta percentages computed by GET /api/admin/metrics (intentionally not yet displayed).

- A sixth dashboard metric card (Total Alerts) beyond the five documented.

Impact: Minor - record in the Final Report's additions list; no baseline amendment required.

3. Design Changes (Baseline Replaced)

B1  App-Required Access Model - No Browser Path to the Destination

Baseline:

- PMP WBS 5.1.2 promises a browser “Continue to destination” button.

- Design 5.2.2 states a validated browser user “is only allowed to continue to the destination URL if the QR code is valid and active.”

- Design 6.5 further records that the client preferred not to force an app, because a browser path widens adoption.

As built:

- A browser scan is redirected to /landing/?status=&reason=&apk= and the destination URL is deliberately never passed to the browser (backend/src/routes/qr.js, browser branch of GET /verify, lines 63-73; the in-code comment reads verbatim: “destinationUrl is deliberately NOT passed - browser users never receive the destination (app-required model)”).

- The landing page shows the full green/red verification verdict plus an APK-download call-to-action; declining shows a pop-up explaining the app is required.

- Only the mobile app can reach destination URLs.

Rationale:

- Reaching the destination is the reward of the security model; granting it to unauthenticated browsers removes the incentive that drives adoption of the secure scanning app (risk R10).

- Every browser scan still receives full server-side verification, so no user is left unprotected.

Impact:

- This is the single most fundamental divergence and it contradicts three baseline locations at once: PMP WBS 5.1.2, Design 5.2.2 and Design 6.5. All three must be amended before Sprint 5 test cases are finalised.

- ACTION REQUIRED: because Design 6.5 records a contrary client preference, and the PMP change-management process requires client approval for behaviour-changing modifications, written client approval of the app-required pivot must be located in the meeting minutes - or obtained at the 22 July demonstration - and cited in the Final Report.

B2  Frontend Technology Stack (Corrected in v2.0)

Baseline:

- PMP specifies “React” with axios, react-router-dom and recharts.

- Design 3.3/6.3 lists Express v4, Prisma v5, React Native 0.73, axios, and helmet+cors middleware.

- Internal planning originally assumed Create React App with React 18.2.0 pinned.

As built:

- Admin dashboard and landing page are Figma Make exports adopted as the codebase: Vite build tooling, React 19.2 (admin-web 19.2.7, landing-web 19.0), Tailwind CSS v4, shadcn/ui (Radix UI), Recharts, react-router 7; the admin app is plain JSX, not TypeScript.

- Backend runs Express 5.2.1 (the SPA fallback uses Express-5-compatible middleware instead of app.get('*')) with Prisma 7 (connection URLs in prisma.config.ts, @prisma/adapter-pg driver).

- Mobile is React Native 0.86 on Expo SDK 57 with expo-router.

- All HTTP uses fetch - axios is not installed; the CSV export is a raw fetch blob download.

- helmet is documented but NOT installed (see Limitation D6).

Rationale:

- The team's completed Figma designs exported directly to working component code.

- The PMP mandates only 'React', so no client-facing commitment was broken; version drift beyond the Design tables is normal over a seven-week build but must be recorded.

Impact:

- Design 3.3/6.3 stack tables must be rewritten to the actual versions.

- v2.0 of this register corrects v1.0, which wrongly recorded React 18.3.1 (the original Figma Make peer dependency, since upgraded).

B3  QR Generation - Admin-Only, Revised Expiry Options, Label Field

Baseline:

- PMP WBS 4.3 lists POST /api/qr/generate with no access restriction.

- Design 5.2.1/7.4.3 specifies an expiry dropdown of 1, 48, 72, 168 hours and inputs of destination URL + expiry only.

As built:

- Generation requires an authenticated administrator (requireAdmin).

- The dropdown offers 24, 48, 72, 168 hours - the 1-hour option was replaced with 24 hours - while the backend accepts any whole value from 1 to 8760 hours (the dropdown is a frontend constraint only).

- An optional Label field (max 120 characters) was added.

Rationale:

- Open generation would let anyone mint signed codes under the organisation's trust umbrella - the exact abuse the platform exists to prevent.

- The flexible backend range keeps the API future-proof while the UI stays simple.

Impact: Design 5.2.1/7.4.3 and the API documentation must be updated; test cases should cover both the UI values and the backend boundary (1-8760).

B4  Mobile Verification - User-Agent Branching Replaced by an Authenticated Endpoint

Baseline: PMP WBS 3.5/6.6 and Design 5.2.2/6.1.3: a single verify endpoint inspects the User-Agent header (SecureQRApp/1.0) and branches between app and browser responses.

As built:

- Two endpoints: the public GET /api/qr/verify?token= (qr.js line 58) serves standard camera scans and the landing-page path unchanged; the dedicated authenticated POST /api/qr/verify/mobile (line 46, behind requireAuth) serves the app, returns JSON, and attributes the scan to the signed-in account (ScanLog.userId).

- The User-Agent string is stored in ScanLog for telemetry only and is never used for authorisation.

Rationale:

- A User-Agent header can be forged by anyone - trusting it for identity would be like trusting anyone in a postal uniform to be a postal worker.

- Real JWT authentication protects app scans and is also what makes server-backed scan history (B5) possible.

Impact:

- Documents should retain 'user-agent detection' only as a channel-identification note with an explicit statement that it is never an authorisation mechanism.

- Backward compatibility for standard scanners is unaffected because the public endpoint is unchanged.

B5  Scan History Stored Server-Side per User

Baseline: Not in any baseline document; interim development planning placed personal scan history in on-device storage (AsyncStorage).

As built: GET /api/scans/history (authenticated) returns the signed-in user's scans, backed by the indexed ScanLog.userId column; the app's history screen reads the server.

Rationale:

- Server-side history survives reinstalls and device changes and reuses telemetry the server already records.

- The privacy trade-off is acceptable because history exists only for authenticated app users.

Impact: Interim documentation describing AsyncStorage is obsolete and must be corrected (CLAUDE.md).

B6  Registration Flow - Confirmation Before Sign-In

Baseline: Not specified; the mock UI auto-signed users in immediately after registration.

As built: Successful registration redirects to the login screen with a success banner; the user signs in explicitly. The register endpoint returns the created user without a session token.

Rationale: Matches the backend's natural contract and gives explicit confirmation that the account was created.

Impact: User Manual screenshots must show the confirmation flow.

B7  Infrastructure - Hosting, Database Connections, File Storage

Baseline: PMP 10 anticipated free-tier hosting and a free-tier cloud database without naming providers; Design mentions PostgreSQL 15 (managed) and Render/Railway.

As built:

- A single Render service (free tier, main branch) serves the API, the landing static build under /landing, and the admin SPA at the root.

- Database is Supabase PostgreSQL through Prisma 7 with two connection strings identified by hostname, never by port: DATABASE_URL via the session pooler (pooler.supabase.com:5432) for runtime, DIRECT_URL via the direct host (db.<ref>.supabase.co:5432) for migrations.

- Alert photos are uploaded to the Supabase Storage bucket alert-photos with only the URL stored, because Render's filesystem is ephemeral.

Rationale:

- Satisfies the zero-budget constraint.

- The hostname rule replaced an earlier port-based rule invalidated by Supabase's February 2025 pooler change; memory-storage photo handling prevents evidence loss on redeploy.

Impact: Installation and Deployment Guide must record the connection rules, the Render build command (which builds and copies both web bundles), and the storage design.

B8  QR Display Page Absorbed into the Admin SPA

Baseline: PMP 4.1.3 and Design promise “three web pages: Landing, QR Display, Admin Dashboard,” with the Display Page as a standalone page shown after generation.

As built:

- There is no standalone QR Display Page. The generated QR image and its details are absorbed into the admin SPA as the generation-result modal and the QR detail view (QRCodeDetailPage.jsx), with Download PNG and Print.

- Deployment is a Landing static build plus the admin SPA, both served by one Express service.

Rationale: The display function only ever serves authenticated administrators, so it belongs inside the authenticated SPA; a standalone public page would add an unauthenticated surface for no benefit.

Impact: The 'three web pages' phrasing in PMP 4.1.3 and the Design page inventory must be re-worded to 'two delivered web surfaces; display functionality integrated into the dashboard.'

4. UI Scope Reductions (Deliberate, vs Design 7.4)

C1  Users Page (7.4.4)

Documented:

- Four metric cards (Total / Active / Suspended / 2FA Enabled).

- Four roles (Super Admin / Admin / Reviewer / User), status badges, 'QR Managed' and 'Alerts Reviewed' counts, and a Suspend action.

As built:

- Two roles only (user / admin); suspension, 2FA and user-status management are not built (suspend logic survives only as commented-out code).

- Added beyond the document: role change with the last-admin guard, self-role-change block, and user deletion.

Disposition: Suspend/Restore requires auth-middleware changes and is deferred to future-work.md.

C2  Settings Page (7.4.5)

Documented: 2FA toggle, login-history table, notification toggles, Account Summary, and a Danger Zone (Revoke All Sessions, Export Account Data).

As built:

- Profile editing (name / phone) and password change only; login history is reduced to a single lastLogin value.

- 2FA and e-mail notifications are future-work items.

Disposition: Deferred; note that authVersion (A2) already delivers the substance of 'revoke all sessions' on password change.

C3  Alerts Page (7.4.3)

Documented: Status filter All / New / Reviewed / Resolved, a 'Mark as Reviewed' action, an Admin-notes field, and a GPS map link.

As built:

- A two-state model: new / resolved, resolve-only - reopening is rejected by the server.

- The Reviewed stage and adminNotes were removed as dead mock code; GPS is displayed as formatted coordinates.

Disposition: Amend 7.4.3 to the two-state vocabulary; a map link remains a possible future enhancement.

C4  Dashboard, Search and Pagination Details

Documented vs built:

- Dashboard: five metric cards documented, six implemented (Total Alerts added); the four scan-volume ranges (1h/24h/1w/1M) match.

- Search: documented 'by QR_ID or URL', implemented over label + destinationUrl (not the ID).

- Pagination: documented page sizes 10/25/50, implemented default 20 with maximum 100.

Disposition: Update the Design UI specification to the delivered values; none of these affect client-facing promises.

5. Deferred Features (Documented in future-work.md)

- Account suspend/restore (User.status) - requires schema migration and auth-middleware changes.

- E-mail notification preferences - requires nodemailer infrastructure.

- Admin-initiated password reset for other users.

- Two-factor authentication.

- Real e-mail delivery for password reset - demo mode returns the reset link in the API response.

- Migration to Supabase Auth - rejected: QR tokens cannot be issued by Supabase Auth and the custom JWT system is complete.

Per the original baselines, the ISO/IEC 18004 standard extension and the time-based redirect service remain out of scope as agreed (client-brief Optional Extras).

6. Known Limitations of the Delivered System

D1  Post-Install Token Handoff

Limitation: After a browser user installs the app from the landing page, the originally scanned token cannot be handed to the app automatically; the user must rescan the physical code.

Disposition: Accepted; deep-link handoff is a future enhancement.

D2  iOS Users Cannot Reach Destinations

Limitation: The app is a direct Android APK (per the Android-first, no-store scope). iOS users see the browser verdict but, under the app-required model (B1), can never reach the destination URL.

Disposition: Accepted and documented; iOS distribution was excluded by the PMP itself.

D3  Baseline Amendments Outstanding for the Access Model

Limitation: PMP WBS 5.1.2, Design 5.2.2 and Design 6.5 all still describe browser access to the destination; Sprint 5 test cases derived from them will fail by design until amended.

Disposition: Action item with client-approval verification - see B1 and Section 10.

D4  Logical vs Physical Schema Types

Limitation: The Design Document specifies uuid, varchar and CHECK constraints; the live Prisma-managed schema maps these to text columns with application-level validation.

Disposition: Documented as logical-vs-physical in schema-reconciliation.md; summarise in the Final Report.

D5  Cold-Start Latency on Free-Tier Hosting

Limitation: Render's free tier sleeps idle services; the first request after idling can take roughly 30 seconds, temporarily exceeding the 3-second redirect metric. Subsequent requests meet the target.

Disposition: Accepted as a hosting-tier constraint consistent with the zero-budget requirement. Mitigation for demonstrations: pre-warm GET /api/health.

D6  helmet Documented but Not Installed

Limitation: Design 6.3 lists helmet under secure HTTP headers, but backend/src/app.js applies cors() only and helmet is absent from package.json.

Disposition: Adding it is one dependency and one line (app.use(helmet())), but Content-Security-Policy compatibility with the admin SPA and the landing static build must be verified first. With the client demo on 22 July, the safe window is during Sprint 5 after the demo - or remove helmet from the Design stack table.

D7  Two Documented Mitigations Not Implemented

Limitation:

- R&A FR-03's destination allowlist (“server-side setup of authorized destination targets”) is not implemented - any http/https URL is accepted at generation; risk is low because generation is admin-only.

- R&A FR-07's manual-location fallback when GPS is denied is not implemented - GPS is simply optional.

Disposition: Either implement or formally re-scope both requirements in the R&A amendment.

D8  No Downtime Monitoring

Limitation: Design 6.4.6 promises an alert if downtime exceeds three minutes; no monitoring is implemented. Database backups are delegated to managed Supabase.

Disposition: Record as an operational limitation; free-tier hosting offers no monitoring hooks.

7. Internal Inconsistencies Within the Baseline Documents

Found during code review - these are defects of the documents themselves, independent of the implementation:

- Design 4.3 (Photo BYTEA) contradicts Design 6.5 (cloud object storage with URL in DB); 4.3 must be corrected.

- Design 6.4.1 claims city-level GPS is recorded, but administrators must physically locate tampered codes in the field - precise Float coordinates are the correct behaviour; amend the document, not the code.

- Design 7.5 Input Specifications duplicates the same table several times (copy-paste editing error).

- Design 4.6 CRUD matrix contains no Delete operation anywhere, yet user deletion exists; admin-side user creation is also missing.

- Design data dictionary omits the email column - the login identifier - entirely (see A4).

- R&A 4.1 defines the User actor as unauthenticated, which no longer holds (see A1).

8. R&A Requirements Traceability

| Requirement | Verdict | Evidence / Notes |
| --- | --- | --- |
| FR-01 Secure QR generation (JWT: expiry, URL, timestamp; keys in .env) | Met, exceeded | tokenService.js; QR_JWT_SECRET and AUTH_JWT_SECRET are separate secrets - stronger than the document requires. |
| FR-02 Validation & authentication (signature, expiry, blacklist checked before DB) | Met, exceeded | verifyService.js: JWT verification runs before any database query; authVersion adds replay revocation. |
| FR-03 Redirect system | Changed / partial | Browser users never reach the destination (B1). The documented destination allowlist is not implemented (D7); risk low because generation is admin-only. |
| FR-04 Mobile application | Met (except release) | Scan, verify, five result statuses implemented; only the EAS APK release step remains. |
| FR-05 Blacklist control | Met | A status change takes effect on the very next scan (verifyService.js). |
| FR-06 Admin dashboard (RBAC) | Met, exceeded | requireAdmin guards every admin route; last-admin guard and self-role-change block are extra protections. |
| FR-07 Tamper reporting (multipart, 5 MB limit) | Met (fallback gap) | 5 MB cap and image-only MIME filter implemented exactly; GPS manual-entry fallback not implemented (D7). |
| FR-08 Scan analytics | Met, exceeded | Every scan including failures is logged; four-range bucketed charts exceed the documented scope. |
| NFR: redirect within 3 seconds | Conditional | Logic meets the target; Render cold start can violate it on the first request (D5). Pre-warm /api/health before demos. |
| NFR: backups, recovery, monitoring | Delegated / partial | Backups delegated to managed Supabase; the 3-minute downtime alert is not implemented (D8). |
| NFR: HTTPS, bcrypt, RBAC, upload validation | Met | All verified in code review. |

9. Consolidated Change Register

| ID | Area | Baseline | As-Built (21 Jul 2026) | Category |
| --- | --- | --- | --- | --- |
| A1 | Authentication | End-user login excluded; User = unauthenticated | Full custom auth incl. channel-aware reset; reporting requires sign-in; browser path account-free | Scope Addition |
| A2 | Token design | Single JWT approach | Dual secrets + authVersion revocation | Scope Addition |
| A3 | Administration | None | Users page, roles, last-admin guard, admin-created accounts, deletion | Scope Addition |
| A4 | Database | 4 entities, NOT NULL throughout | 5 tables; email added; photoUrl; nullable FKs for auditability; label; userId | Scope Addition |
| A5 | QR lifecycle | Blacklist check; images stored once | 4-state lifecycle, lazy sweep, terminal expiry, report-promotion guard, on-demand PNG | Scope Addition |
| A6 | Operations | - | CSV export, Recent Activity feed, 6th metric card, computed deltas | Scope Addition |
| B1 | Access model | Browser 'Continue' (WBS 5.1.2; Design 5.2.2/6.5) | App-required; browser gets verdict + APK CTA only | Design Change |
| B2 | Tech stack | React/CRA; Express 4; Prisma 5; RN 0.73; axios; helmet | Vite + React 19.2 + Tailwind v4 + shadcn/ui (JSX); Express 5; Prisma 7; RN 0.86/SDK 57; fetch; no helmet | Design Change |
| B3 | QR generation | Open endpoint; 1/48/72/168 h; URL+expiry | Admin-only; 24/48/72/168 h UI, 1-8760 h API; label field | Design Change |
| B4 | App verification | User-Agent branching | Authenticated POST /api/qr/verify/mobile; UA telemetry-only; public GET unchanged | Design Change |
| B5 | Scan history | Not documented (interim: on-device) | Server-side per-user history | Design Change |
| B6 | Registration UX | (mock auto-sign-in) | Register, then success banner, then explicit login | Design Change |
| B7 | Infrastructure | Unnamed free tier; PostgreSQL 15 | Render single service; Supabase + Prisma 7; hostname-based connections; Storage for photos | Design Change |
| B8 | Page inventory | Three standalone web pages | Two surfaces; Display absorbed into admin SPA (modal + detail view) | Design Change |
| C1-C4 | Dashboard UI | 7.4 full spec (2FA, suspend, Reviewed, notes...) | Two roles, two alert states, reduced Settings; extra guards added | Scope Reduction |
| C(def) | Deferred set | - | Suspend/restore, e-mail prefs, admin reset, 2FA, real e-mail, Supabase Auth | Deferred |
| D1-D8 | Limitations | - | Token handoff, iOS reach, baseline amendments, logical-vs-physical, cold start, helmet, allowlist/GPS fallback, monitoring | Known Limitation |

10. Prioritised Documentation Actions (Before 1 August)

- 1. Amend the access-model baselines together - PMP WBS 5.1.2, Design 5.2.2, Design 6.5 - and re-baseline the affected Sprint 5 test cases. VERIFY OR OBTAIN written client approval for the app-required pivot (Design 6.5 records a contrary client preference; the 22 July demo is the natural approval point).

- 2. Regenerate the Design 4.3 data dictionary and ERD: add email and ActivityLog, replace Photo BYTEA with photoUrl, update status vocabularies (new/resolved; active/blacklisted/suspicious/expired), record relaxed NOT NULL constraints, fix the Created_By/User_ID naming inconsistency.

- 3. Amend R&A: re-word 4.1 actor definitions (authentication now required for reporting); re-scope or implement the FR-03 destination allowlist and the FR-07 GPS manual-entry fallback.

- 4. Rewrite the Design 3.3/6.3 technology tables: Express 5, Prisma 7, RN 0.86 / Expo SDK 57, React 19.2, fetch instead of axios; either install helmet (after the demo, with CSP verification) or remove it from the table.

- 5. Final Report known-limitations section: D1-D8 as listed, including cold start vs the 3-second target, no downtime monitoring, precise (not city-level) coordinates, and the absent GPS manual fallback.

- 6. Correct interim documentation (CLAUDE.md): React 19.2 not 18.3.1; server-side scan history not AsyncStorage; User-Agent is telemetry-only, not the app identification mechanism.